## Slide 1: Implementation Status of Planned Activities for Q3 2026
# | Achievements | Status | Comments (if any)
6 | Commence development of phase 1 of the Polio Geo Intelligence Canopy (PolGIC) following the completion of the APW | Achieved | PolGIC APW signed, Formal project kickoff held, Technical workshop held,Initial dataset introduction held,Portal access was available for further Esri review and first month report shared
7 | Complete and submit the grant closure report for the WHO AFRO GIS Centre Support Grant |  | 
8 |  |  | 
9 |  |  | 
10 |  |  | 

## Slide 2: Key Activities Implementations in the Past Quarter - Unplanned but Achieved
# | Achievements | Comments supporting prioritization
1 | IM Workflow Automation: end-to-end pipeline — ONA API fetch → repository build → geoname standardization → SharePoint upload → Intelligence Report/Brief/Deck generation; scheduled unattended runs (Mon-Fri); automated failure alerting. | Eliminates a previously manual, multi-step data-consolidation and reporting process; replaces ad hoc report generation with a reliable scheduled cadence and a monitored safety net so a failed run is caught the same night rather than discovered days later.
2 | LQAS Pipeline Automation: manual Power BI export → direct GPEI REST API refresh; automated weekly scheduling (Mon); data validation safeguards (schema/status checks, row-count-collapse detection, auto-backup). | Removes a recurring manual download step that was easy to forget and prone to going stale; added data-quality safeguards (column and status checks, row-count-collapse detection, automatic backups) so a bad fetch can never silently corrupt the production lookup file.
3 | AFRO-SIA Dashboard — SIA Scope Data Pipeline: root-caused and resolved critical data-completeness defect in GPEI scope ingestion (silent multi-country record loss); validated via cross-source comparison and API-level diagnostics. | Root-caused through systematic validation against the original manual GPEI export and direct API-level investigation. Left unaddressed, SIA scope coverage maps and completeness metrics used for program monitoring would have remained materially understated ahead of upcoming reporting cycles.
4 | AFRO-SIA Dashboard — Scope Summary Map: new feature — period-level scope aggregation across rounds; automated round-consistency footnotes; PNG/PDF export. | Improves the speed and reliability of period-over-period SIA geographic coverage reporting and automatically flags rounds where scope or vaccine composition changed within the same country/period, work previously done through manual cross-checking.